## Sheet1
Task (Week start date) | Week 4 (9/7) | Week 5 (9/13) | Week 6 (9/20) | Week 7 (9/27) | Week 8 (10/04) | Week 9 (10/11) | Week 10 (10/18) | Week 11 (10/25) | Week 12 (11/01) | Week 13 (11/08) | Week 14 (11/15) | Week 15 (11/22) | Week 16 (11/29)
Startup (Everyone)
Research (Everyone)
XML Parser Developers
JSON Parser (Developers)
FHIR Server Validation (Developers)
DB Creation (Developers)
Populate DB (Developers)
QA (QA)
Visualization (PM)
Final Submittals (PM)
Owner Evaluation (PM)
Sprint Activity Due (PM) | #1 |  | #2 |  | #3 |  | #4 |  | #5 |  | #6 |  | #7, #8